## Master Cobra Processing Steps
ID | Work Instruction | Checklist Steps | Folder Location | Notes |  | Person Responsible
DI-CP001 | Set-Up for Current Month | Set-Up for Current Month Processing |  |  | Good
DI-CP002 | Advance Calendar | Advance the Cobra Project Calendar |  | change fiscal & planning horizon calendars; 06 & 19 | Good
| Material Activity Mappings | Material Activity Mappings P6 to Baan |  | Need final IT Layout Mapping Report from Scheduling | Need work instruction/clarifications | Erik
| Verify Presence of Material Reports for CAMs | Open PO, Committed, Open Buy Report | Y:\EVMS\CAM_Notebooks\04 - Material CAM Meetings, Material Reports\Material Reports\04xx LCS xx USS xxxxxxx Material Reports\20yy | Y:\EVMS\CAM_Notebooks\04 - Material CAM Meetings, Material Reports. Tom Hannon does this | Good
| Verify Presence GL Detail Report for CAMs | General Ledger Detail Report; after Baan Lock | Y:\EVMS\CAM_Notebooks\04 - Material CAM Meetings, Material Reports\Material Reports\04xx LCS xx USS xxxxxxx Material Reports\20yy | Finance needs to lock Baan; tfgld9516m000; same location as above | Good
| Update Contract Budget File | Update Contract Budget File | Y:\Program Management\Contract File (Budgets)\LCS Program |  | Need work instruction/clarifications (Rework) | Matt
DI-CP010 | Export Labor & Material Actuals from Baan | Export Labor & Material Actuals from Baan | Y:\Program Management\Cobra Processing\LCSxx\04xx\04xx Actual Cost Files |  | Completed | Dylan
DI-CP011 | Update Estimated Actuals & Material Adjustment Logs | Determine Rollover Estimated Actuals & Material Adjustments | Y:\Program Management\Cobra Processing\LCSxx\04xx\04xx Actual Cost Files
DI-CP013 | Load Baseline | Validate P6 Baseline to Contract Budget File |  |  | Completed
Identify Baseline Changes
Load Baseline Changes into Cobra
|  | Reconcile Baseline to P6 & Contract Budget File | Y:\Program Management\Cobra Processing\LCSxx\04xx\04xx 20yy\04xx mmm 20yy Cobra Processing\04xx mmm 20yy Reconciliations
DI-CP026 | Validate Time-phased BCWS on LM Files | Run Time-phased report for BCWS to see if there are any history changes | Y:\Program Management\Cobra Processing\LCSxx\04xx\04xx 20yy\04xx mmm 20yy Cobra Processing\04xx mmm 20yy Reconciliations
| Run Validity Check in Cobra | Run Validity Check |  |  | Need work instruction | Dan
| Notify WAD/CAM Admin for Baseline Reconciliation | Generating WAD worksheet & CAM Code Changes | Y:\Program Management\Cobra Processing\LCSxx\04xx\04xx 20yy\04xx mmm 20yy Cobra Processing\04xx mmm 20yy Working Files
DI-CP017 | Load Baseline Codes | Load and Validate Material Code Assignments |  | Can do after baseline is loaded; backup Cobra following reconciliation
DI-CP040 | Update Cobra Baseline Log | Update Cobra Baseline Log with Change Numbers |  |  | Completed | Dan
DI-CP009 | Update LM PCW Spreadsheet | Update LM PCW Spreadsheet with UB changes | Y:\Program Management\Cobra Processing\LCSxx\04xx\04xx 20yy\04xx mmm 20yy Cobra Processing\04xx mmm 20yy Reconciliations
| Prepare WAD Worksheet | Prepare Work Authorization Documents (WADs) | Y:\Program Management\Cobra Processing\LCSxx\04xx\04xx 20yy\04xx mmm 20yy Cobra Processing\04xx mmm 20yy Working Files | Y:\EVMS\CAM_Notebooks\01 - Contract SOW, WBS, OBS, RAM, CAM Assignments | Need work instruction | Greg
DI-CP006 | Update Log Analysis Spreadsheet | Update Log Analysis Spreadsheet | Y:\Program Management\Cobra Processing\LCSxx\04xx\04xx 20yy\04xx mmm 20yy Cobra Processing |  | Update | Dan
DI-CP008 | Update Cobra Program Log Transactions | Enter Cobra AUW, MR, and Mod Transactions for BCRs and PCWs |  |  | Completed | Dylan
Reconcile Cobra and Log Analysis Spreadsheet
| Load CAM Codes | Load CAM Codes into Cobra | Y:\Program Management\Cobra Processing\LCSxx\04xx\04xx 20yy\04xx mmm 20yy Cobra Processing\04xx mmm 20yy Working Files |  | Needs work instruction | Greg
| Prepare RAM | Prepare Responsibility Assignment Matrix (RAM) | Y:\EVMS\CAM_Notebooks\01 - Contract SOW, WBS, OBS, RAM, CAM Assignments\RAM - Responsibility Assignment Matrix | Y:\EVMS\CAM_Notebooks\01 - Contract SOW, WBS, OBS, RAM, CAM Assignments | Completed | Erik
DI-CP023 | Load Actuals into Cobra | Prepare Actuals Load File for Cobra | Y:\Program Management\Cobra Processing\LCSxx\04xx\04xx Actual Cost Files | Baan Download file into Cobra (1 EA and 1 AC) | Completed | Dylan
Load All Actual Costs
Reconcile Cobra Actuals to BAAN and Estimated Actuals Log
DI-CP012 | Prepare P6 Material Actuals Import File | Prepare material actuals file for P6 | Y:\Program Management\Cobra Processing\LCSxx\04xx\04xx Actual Cost Files | CP023 needs to be done first (1 amount for each activity)
DI-CP018 | Run Preliminary Material CAM Reports | Run Preliminary CAM Material Reports and Notify CAMs | Y:\EVMS\CAM_Notebooks
| Prepare Preliminary MEAC | Prepare Preliminary MEAC for CAM Notebooks | Y:\EVMS\CAM_Notebooks\04 - Material CAM Meetings, Material Reports\Material Reports\04xx LCS xx USS xxxxxxxxx Material Reports\20yy |  | Needs work instruction | Erik
| Prepare and Submit Material Status | Conduct Material CAM EAC/Status Meetings | Y:\EVMS\CAM_Notebooks\04 - Material CAM Meetings, Material Reports\CAM Meeting Questions & Notes
|  | Update Estimated Actuals Log | Y:\Program Management\Cobra Processing\LCSxx\04xx\04xx Actual Cost Files
Prepare and Submit Material Status and Final Actual Cost Updates to Scheduling
DI-CP023 | Reload Actuals into Cobra (if needed for Estimated Actual Updates) | Prepare Actuals Load File for Cobra | Y:\Program Management\Cobra Processing\LCSxx\04xx\04xx Actual Cost Files | Baan Download file into Cobra (1 EA and 1 AC)
Load All Actual Costs
Reconcile Cobra Actuals to BAAN and Estimated Actuals Log
| Enter Material Status Updates in Cobra | Update Material Status/EACs in Cobra |  |  | Needs work instruction | Tom
DI-CP016 | Load Labor Status | Load Labor Status/Forecast |  | Need Status File
Calculate Earned Value
|  | Reconcile Labor & Material Status to P6 | Y:\Program Management\Cobra Processing\LCSxx\04xx\04xx 20yy\04xx mmm 20yy Cobra Processing\04xx mmm 20yy Reconciliations
| Run Validity Check in Cobra | Run Validity Check |  |  | Need work instruction | Dan
DI-CP017 | Load CP Codes - Status | Load CP Code Assignments |  | CP codes after Status load; backup Cobra following reconciliation | Review config file
| Notify WAD/CAM Admin for Status Reconcilation | Perform Cap Explanations Log | Y:\EVMS\CAM_Notebooks\06 - CAP Explanations, Variance Reviews, Corrective Actions\CAP Explanations | Data Integrity File
| Prepare Final MEAC | Prepare Final MEAC | Y:\EVMS\CAM_Notebooks\04 - Material CAM Meetings, Material Reports\Material Reports\04xx LCS xx USS xxxxxxxxx Material Reports\20yy |  | Work instruction included in preliminary MEAC WI | Erik
DI-CP026 | Run and Validate LM Data Files | Run Batch LM Files | Y:\EVMS\CAM_Notebooks\LM Files
|  | Perform Retroactive Change Reconciliation | Y:\Program Management\Cobra Processing\LCSxx\04xx\04xx 20yy\04xx mmm 20yy Cobra Processing\04xx mmm 20yy Reconciliations
DI-CP025 | Run Final CAM Reports | Run Final CAM Reports and notify CAMs | Y:\EVMS\CAM_Notebooks
DI-CP009 | Update LM PCW Spreadsheet | Update LM PCW Spreadsheet | Y:\Program Management\Cobra Processing\LCSxx\04xx\04xx 20yy\04xx mmm 20yy Cobra Processing\04xx mmm 20yy Reconciliations |  | Update Work Instruction | Michelle
DI-CP029 | Update BAC/EAC Spreadsheet | Update BAC/EAC Comparison Spreadsheet | Y:\Program Management\Cobra Processing\LCSxx\04xx\04xx 20yy\04xx mmm 20yy Cobra Processing\04xx mmm 20yy Reconciliations |  | Completed | Dylan
DI-CP027 | Prepare Program Reports for PM Review | Update EAC Recommendations Spreadsheet | Y:\Program Management\Cobra Processing\LCSxx\04xx\04xx 20yy\04xx mmm 20yy Cobra Processing\04xx mmm 20yy Working Files |  | Completed | Dylan
Update Cobra Contract Budget Information and EACs
|  | Run and Print CPR 1, CPR 2, CPR3, and CPR 4 Batch reports | Y:\EVMS\CAM_Notebooks\CPRs
Validate CPRs
| Review Program Reports with PM | Review Status with PM
Make Updates, Rerun, Print and Validate Reports if Necessary
Review Final CPRs with PM if Necessary
DI-CP032 | Run MR & UB Log | Run MR and UB Log | Y:\EVMS\CAM_Notebooks\CPRs
| Submit CPR Data Files to LM | Submit CPRs, LM Data Files, MR & UB Logs, and PCW Spreadsheet |  | Make sure you're using the correct naming conventions for the files to LM
| Notify WAD/CAM Admin for CPR 1 - 4 Submittal | Start wInsight Files | Y:\EVMS\CAM_Notebooks\07 - IBRs, Surveillance\Navy Surveillance\20yy\mmm
| Prepare Financial Reports | Run Financial Batch Reports and notify Finance | Y:\EVMS\CAM_Notebooks\Finance Reports
DI-CP042 | Prepare and Submit CPR Format 5 | Run EVM Analysis Report for CPR 5 Variances | Y:\Program Management\Cobra Processing\LCSxx\04xx\04xx 20yy\04xx mmm 20yy Cobra Processing\04xx mmm 20yy Working Files
|  | Prepare CPR 5 Template | Y:\EVMS\CAM_Notebooks\CPRs
Review CAM VARs
|  | Prepare CPR 5 | Y:\EVMS\CAM_Notebooks\CPRs
Review CPR 5 with PM
|  | Submit CPR 5 | Y:\EVMS\CAM_Notebooks\CPRs
Notify person responsible for Corrective Action Log that Format 5 is complete

## Sheet2
Baseline Reconciliation Checklist
Validate Baseline to Contract Budget File
Reconcile WBS 4 Budgets (reconciliation file)
Check for history changes
Run Validity Check in Cobra
Status Reconciliation Checklist
Validate WBS 4 Status to p6 (Actuals, Progress, ETC/EAC)
Check for history changes
Run Validity Check in Cobra