## Master Cobra Processing Steps
ID | Work Instruction | Checklist Steps | Notes
WI-CP001 | Set-Up for Current Month | Set-Up for Current Month Processing
WI-CP002 | Advance Calendar | Advance the Cobra Project Calendar
WI-CP003 | Setup CAM Filters and Reports | Setup CAM Filters and Reports | Dan Does this.
| Material Activity Mappings | Material Activity Mappings P6 to Baan | Need final IT Layout Mapping Report from Scheduling
| Prepare Open PO Report for CAMs | Run Open PO Report | Y:\EVMS\CAM_Notebooks\04 - Material CAM Meetings, Material Reports. Tom Hannon does this
| Prepare Committed Report for CAMs | Run Committed Report | Should be ran on Monday after EV ME; tdpur9425m000; same location as above. Tom Hannon does this.
| Prepare Open Buy Report for CAMs | Run Open Buy Report | tiitm9408m000; compared to 0465; select last option; B2Win; location as above. Tom Hannon does this.
| Prepare IMS Exception Report for CAMs | IMS Exception Report | tdpur9434m000; same location as above
| Prepare GL Detail Report for CAMs | Run General Ledger Detail Report | Finance needs to lock Baan; tfgld9516m000; same location as above
| Update Contract Budget File | Update Contract Budget File
| Update PM's BCR Log | Update PM's BCR Log for MR Measurement Burndown
WI-CP010 | Export Labor Actuals from Baan | Export Labor Actuals from Baan
WI-CP010 | Export Material Actuals from Baan | Export Material Actuals from Baan
| Update Estimated Actuals Log | Determine Rollover Estimated Actuals
WI-CP013 | Load Baseline | Validate P6 Labor & Material Baseline to Contract Budget File
Identify Labor & Material Baseline Changes
Load Labor & Material Baseline Changes into Cobra
Reconcile Labor & Material Baseline to P6 & Contract Budget File
WI-CP026 | Validate BCWS on LM Files | Run report for BCWS to see if there are any history changes
WI-CP021 | Update Cobra Baseline Log | Update Cobra Baseline Log with Change Numbers
WI-CP006 | Update Log Analysis Spreadsheet | Update Log Analysis Spreadsheet
WI-CP008 | Update Cobra Program Log Transactions | Enter Cobra AUW, MR, and Mod Transactions for BCRs and PCWs
Reconcile Cobra and Log Analysis Spreadsheet
WI-CP017 | Load All Codes - Baseline | Load and Validate Material Code Assignments | Can do after baseline is loaded; backup Cobra following reconciliation
| Load CAM Codes | Load CAM Codes into Cobra
| Prepare WADs | Prepare Work Authorization Documents (WADs) | Y:\EVMS\CAM_Notebooks\01 - Contract SOW, WBS, OBS, RAM, CAM Assignments
| Prepare RAM | Prepare Responsibility Assignment Matrix (RAM) | Y:\EVMS\CAM_Notebooks\01 - Contract SOW, WBS, OBS, RAM, CAM Assignments
| Prepare Time-phased report for Cobra Budgets | Run Time-phase Reports by WP & CA for Cobra Budget Changes
| Control Account-CAM Listing | Put Control Account-CAM Listing on the Bridge | Put in Control Account Management (CAM)/Baseline Change Request Folder
WI-CP023 | Load Actuals into Cobra | Prepare Actuals Load File for Cobra | Baan Download file into Cobra (1 EA and 1 AC)
Load All Actual Costs
Reconcile Cobra Actuals to BAAN and Estimated Actuals Log
WI-CP012 | Prepare P6 Material Actuals Import File | Prepare material actuals file for P6 | CP023 needs to be done first (1 amount for each activity)
WI-CP018 | Run Preliminary Material CAM Reports | Run Preliminary CAM Material Reports and Notify CAMs
| Prepare Preliminary MEAC | Prepare Preliminary MEAC for CAM Notebooks
| Prepare and Submit Material Status | Perform Heath Check
Conduct Material CAM EAC/Status Meetings
Update Estimated Acutals Log
Prepare and Submit Material Status and Actual Cost Updates to Scheduling
Update Material EAC Status in Cobra
WI-CP023 | Load Actuals into Cobra | Prepare Actuals Load File for Cobra | Baan Download file into Cobra (1 EA and 1 AC)
Load All Actual Costs
Reconcile Cobra Actuals to BAAN and Estimated Actuals Log
WI-CP012 | Prepare P6 Material Actuals Import File | Prepare material actuals file for P6 | CP023 needs to be done first (1 amount for each activity)
| Create BCR for Timephasing Impacts | Create and Process BCR for Timephasing Impacts | Run CPR 3
WI-CP016 | Load Labor Status | Load Labor Status/Forecast | Need Status File
Calculate Earned Value
Reconcile Labor & Material Status to P6
Perform EAC Change Summary
Perform Heath Check
WI-CP017 | Load CP Codes - Status | Load CP Code Assignments | CP codes after Status load; backup Cobra following reconciliation
| CAP Explanations Log | Finalize Cap Explanations Log | Data Integrity File
WI-CP026 | Run and Validate LM Data Files | Run Batch LM Files
Perform Retroactive Change Reconciliation
| Prepare Final MEAC | Prepare Final MEAC
WI-CP025 | Run Final CAM Reports | Run Final CAM Reports and notify CAMs
WI-CP009 | Update LM PCW Spreadsheet | Update LM PCW Spreadsheet
WI-CP027 | Prepare Program Reports for PM Review | Update EAC Recommendations Spreadsheet
Update Cobra Contract Budget Information and EACs
Run and Print CPR 1, CPR 2, CPR3, and CPR 4 Batch reports
Validate CPRs
| DCMA Data Call | EVM Report for DCMA Data
WI-CP029 | Update BAC/EAC Spreadsheet | Update BAC/EAC Comparison Spreadsheet
Complete Program Summary Worksheet
| Review Program Reports with PM | Review Status with PM
Make Updates, Rerun, Print and Validate Reports if Necessary
Review Final CPRs with PM if Necessary
WI-CP032 | Run LM CAP, MR & UB Logs | Run LM CAP Report
Run MR and UB Log
| Submit CPR Data Files to LM | Submit CPRs, LM Data Files, MR & UB Logs, LM CAP Report, and PCW Spreadsheet
| Prepare Financial Reports | Run Financial Batch Reports and notify Finance
| Prepare and Submit CPR 5 | Run EVM Analysis Report for CPR 5 Variances
Prepare CPR 5 Template
Review CAM VARs
Prepare CPR 5
Review CPR 5 with PM
Submit CPR 5
|  | Update Corrective Action Log from Format 5 | Y:\EVMS\Management\PM-Director's VAR Corrective Action Logs