## Master Cobra Processing Steps
ID | Work Instruction | Checklist Steps | Notes
| Material Activity Mappings | Material Activity Mappings P6 to Baan | Need final IT Layout Mapping Report from Scheduling
| Prepare Open PO Report for CAMs | Run Open PO Report | Y:\EVMS\CAM_Notebooks\04 - Material CAM Meetings, Material Reports. Tom Hannon does this
| Prepare Committed Report for CAMs | Run Committed Report | Should be ran on Monday after EV ME; tdpur9425m000; same location as above. Tom Hannon does this.
| Prepare Open Buy Report for CAMs | Run Open Buy Report | tiitm9408m000; compared to 0465; select last option; B2Win; location as above. Tom Hannon does this.
| Prepare IMS Exception Report for CAMs | IMS Exception Report | tdpur9434m000; same location as above
| Prepare GL Detail Report for CAMs | Run General Ledger Detail Report | Finance needs to lock Baan; tfgld9516m000; same location as above
| Update Contract Budget File | Update Contract Budget File
| Update PM's BCR Log | Update PM's BCR Log for MR Measurement Burndown
| Update Estimated Actuals Log | Determine Rollover Estimated Actuals
| Load CAM Codes | Load CAM Codes into Cobra
| Prepare WADs | Prepare Work Authorization Documents (WADs) | Y:\EVMS\CAM_Notebooks\01 - Contract SOW, WBS, OBS, RAM, CAM Assignments
| Prepare RAM | Prepare Responsibility Assignment Matrix (RAM) | Y:\EVMS\CAM_Notebooks\01 - Contract SOW, WBS, OBS, RAM, CAM Assignments
| Prepare Time-phased report for Cobra Budgets | Run Time-phase Reports by WP & CA for Cobra Budget Changes
| Control Account-CAM Listing | Put Control Account-CAM Listing on the Bridge | Put in Control Account Management (CAM)/Baseline Change Request Folder
| Prepare Preliminary MEAC | Prepare Preliminary MEAC for CAM Notebooks
| Prepare and Submit Material Status | Conduct Material CAM EAC/Status Meetings
Update Estimated Acutals Log
Prepare and Submit Material Status and Actual Cost Updates to Scheduling
Update Material EAC Status in Cobra
| Create BCR for Timephasing Impacts | Create and Process BCR for Timephasing Impacts | Run CPR 3
| CAP Explanations Log | Finalize Cap Explanations Log | Data Integrity File
| Prepare Final MEAC | Prepare Final MEAC
| DCMA Data Call | EVM Report for DCMA Data
| Review Program Reports with PM | Review Status with PM
Make Updates, Rerun, Print and Validate Reports if Necessary
Review Final CPRs with PM if Necessary
| Submit CPR Data Files to LM | Submit CPRs, LM Data Files, MR & UB Logs, LM CAP Report, and PCW Spreadsheet
| Prepare Financial Reports | Run Financial Batch Reports and notify Finance
| Prepare and Submit CPR 5 | Run EVM Analysis Report for CPR 5 Variances
Prepare CPR 5 Template
Review CAM VARs
Prepare CPR 5
Review CPR 5 with PM
Submit CPR 5
|  | Update Corrective Action Log from Format 5 | Y:\EVMS\Management\PM-Director's VAR Corrective Action Logs