## Sheet1
Correct? | Document | Check | Correspsonding Document | Location/Notes
| EAC Recommendations | BCWS | CPR 1 | Section 8.g.
| EAC Recommendations | BCWP | CPR 1 | Section 8.g.
| EAC Recommendations | ACWP | CPR 1 | Section 8.g.
| EAC Recommendations | BAC | CPR 1 | Section 8.g.
| EAC Recommendations | MR | CPR 1 | Section 8.f.
| PCW Spreadsheet | Most Likely EAC | EAC Recommendations
| CPR 1 Dollars | Reporting Period Dates |  | Make sure they are correct period
| CPR 1 Dollars | Negotiated Cost | PCW Spreadsheet | Tagret Cost (Baige area before AUW)
| CPR 1 Dollars | AUW | PCW Spreadsheet | AUW Line
| CPR 1 Dollars | Target Profit/FEE | PCW Spreadsheet | Target Profit (Baige area before AUW)
| CPR 1 Dollars | Target Price | PCW Spreadsheet | Target Price (Baige area before AUW)
| CPR 1 Dollars | Estimated Price | PCW Spreadsheet | Bottom highlighted in Green
| CPR 1 Dollars | Contract Ceiling | PCW Spreadsheet | Bottom highlighted in Red
| CPR 1 Dollars | Estimated Contract Ceiling | PCW Spreadsheet | Bottom highlighted in Purple
| CPR 1 Dollars | Contract Budget Base | PCW Spreadsheet | Target Cost (Baige area after AUW)
| CPR 1 Dollars | EAC | EAC Recommendations | Top Right, not Highlighted
| CPR 1 Dollars | Best, Worst, Most Likely EAC | EAC Recommendations | Highlighted in Green, Red, Yellow
| CPR 1 Dollars | Undistributed Budget
| CPR 1 Hours | Estimated Price | PCW Spreadsheet | Bottom highlighted in Green
| CPR 3 | Section 6.b. |  | Make sure says "Baseline Changes for Period"
| CPR 3 | Six Month Forecast |  | Make sure last period says "TC"
| CPR 3 | Six Month Forecast |  | Make sure months and FYs are correct
| CPR 3 | Unidstributed Budget |  | Make sure UB is in 1000's
| CPR 3 | Total Budget Changes |  | Make sure it equals diff of End of Period - Performance
| CPR 4 EAC | Six Month Forecast |  | Make sure last period says "TC"
| CPR 4 BAC | Six Month Forecast |  | Make sure last period says "TC"
| EAC/BAC Comparison | Negotiated Cost | PCW Spreadsheet | Tagret Cost (Baige area before AUW)
| EAC/BAC Comparison | Target Price | PCW Spreadsheet | Target Price (Baige area before AUW)
| EAC/BAC Comparison | AUW
| EAC/BAC Comparison | Best, Worst, Most Likely EAC | EAC Recommendations | Highlighted in Green, Red, Yellow
| EAC/BAC Comparison | MR | CPR 1 | Section 8.f.
| LM Data Files | Dollar/Hrs files Totals | CPR 1 | Check Cumulative values for BCWS files
| LM Data Files | Last Value (Duration) | CPR 3 Header Dates | Last period for ETC, BCWS aligns with CPR3 Dates
| MR/UB Log | Contract Values | Log Analysis Spreadsheet
| Reconciliation | All ACWP Values Reconcile
| Health Check | Look for non-acceptable Exceptions
Signature